## Sheet1
Date | Hours | Activities
2017-01-20 | 1 | Meeting with Group
2017-01-22 | 3 | Learning Java Sever Pages
2017-02-01 | 0.3 | Revising Phase I Document
2017-02-02 | 0.5 | Contribuiting to Phase I Document
2017-02-05 | 0.5 | Revising Phase I Document
2017-02-25 | 1 | Writing SQL for Sale Items
2017-02-26 | 2 | Writing SQL Scripts & Compiling a list of Categories
2017-02-27 | 1 | Writing SQL script for creating Cateogory Table
2017-03-01 | 1 | Updated Cateogories Table
2017-03-02 | 1 | Editing & Contributing to Report
2017-03-31 | 2 | Searched for HTML library for java
2017-03-22 | 2 | Created classes to represent database objects
2017-03-23 | 2 | Writing Database Interface Functions & Organized SQL Scripts
2017-04-07 | 0.5 | Compiled existing SQL scripts into one file
2017-04-09 | 0.5 | Wrote SQL Script for resetting Database
2017-04-11 | 2 | Writing Database Interface Functions & Writing JSP Pages
2017-04-16 | 1.5 | Writing Database Interface Functions
2017-04-17 | 2 | Create Abstract Page Class
2017-04-18 | 1.5 | Writing Database Interface Functions
2017-04-23 | 0.5 | Reviewing Other Group Member's Code
2017-04-27 | 14 | Finishing Code