## Sheet1
Date | Hours | Activities
2017-01-11 | 2 | Design - Setting up Github account, creating templates for progress reports, creating project timeline system.
2017-01-18 | 1 | Design - Revising project timeline system.
2017-01-20 | 1 | Meeting
2017-01-25 | 1 | Design - Perfoming Requirement Analysis
2017-01-30 | 2 | Design - Revising, writing Introduction, and constructing ER Diagrams
2017-02-01 | 1 | Design - Revising
2017-02-04 | 1 | Design - Revising ER Diagrams
2017-02-05 | 1 | Design - Creating cover page and revising
2017-02-24 | 3 | Design - Revising ER Diagrams and Bidding Section
2017-02-25 | 2 | Design - Finished revising ER Diagrams, created complete ER Diagram
2017-02-26 | 0.5 | Design - Revising, testing SQL Database that was created
2017-02-27 | 1 | Design - Fixing teammates SQL DDL.
2017-02-28 | 0.5 | Design - Fixing sales.sql
2017-03-01 | 2.5 | Design - Creating Concept art
2017-03-02 | 1 | Design - Specifying Android application design
2017-03-02 | 2 | Presenting - Creating presentation, revising document